## Slide 1: Tech M – Keysight 5G Projects
Global System Integrator Team
2020
Dan Sinawat

## Slide 2: Tech Mahindra POC Project Plan
Phase 2 – Public Cloud AWS
Public Cloud – AWS
    NFVI Validation – CloudPeak
    5G Core Emulation – LoadCore;
    4G Core Emulation – Ixload VE
    Automation – Test Module Integration
    External integration via REST API with Net.Ops
Phase 1 – Private Cloud Openstack with KVM
  Private Cloud – OpenStack with KVM
    NFVI Validation – CloudPeak
    5G Core Emulation – LoadCore;
    4G Core Emulation – Ixload VE
    Automation – Test Module Integration
    External integration via REST API with Net.Ops

## Slide 3: Automation Architecture
NetOps.ai
4G and 5G Testing
SUT
NVFI
Network VNF
Compute VNF
Other VNF
REST API
Interconnects
Interconnects
Switches
REST API
Interconnects
Typically all in
one location
Keep tools and SUT in same environment
Close to User Access
GUI
NFVi Testing

## Slide 4: Cloud Peak Deployment
Medium Deployment Licensing:
    4 parallel executions ;
    Limits per Test – up to 512 vCPU and 2040GB RAM
Virtual Machines :
  Cloud PEAK Appliance;
  Workload Images

## Slide 5: Cloud Peak + Test Module Deployment Stages
Prepare VM Images
Download CloudPeak VM Images from our Support Portal
https://support.ixiacom.com/software-downloads/234082
Deploy VM on the Public/ Private Cloud infrastructure using our Install Guide
Access Management console via Web Ui
Product Licensing
Integrate Cloud Peak with NFVI Infrastructure
Execute Benchmark Tests
Add Test Modules for 4G /5G Testing and integrate Test Module with Ixload VE and 5G LoadCore
REST API Automation integration with external Net.Ops Orchestrator
Automate Tasks to automatically execute test cases

## Slide 6: Ixload VE Deployment
IxLoad Client – Windows OS – for GUI Manual Config
Ixload VE Virtual Machines
    Ixload Virtual Chassis
  Ixload Load Module
  Ixload VE Tier4 license need to emulate 4G LTE Core Nodes
  Network interfaces – 1G /10G
  Licensing - Ixload Tier 4 10G Licenses
  Optional licensing for Diameter

## Slide 7: Ixload VE Deployment Stages Overview
Prepare VM Images
Download IxLoad Images from our Support Portal https://support.ixiacom.com/ixvm-ixos-910-ixnetwork-910-ixload-910
Deploy VM on the Public/ Private Cloud infrastructure using our Install Guide
Product Licensing
Access Virtual Chassis via Web Ui and attach one or more Virtual Load Modules and port
Connect from Ixload Windows Client GUI to the Virtual Chassis on File-> Ports -> Add Chassis and manual test Ixload functionalities
Deploy Test Modules in CloudPeak /IxSuiteStore with predefined 4G EPC test cases ;
Run Test cases from the Test Module Library
REST API automation integration with external Net.Ops Orchestrator
Automate Task from Net.Ops to execute Test Cases

## Slide 8: 5G Load Core
5G LoadCore Virtual Machines :
  Middleware VM
    4 x vCPU
    8GB RAM
    30 GB HDD
  Agent VM
    4 x vCPU;
    8GB RAM;
    30 GB HDD
  License Sever VM
    2vCPU;
    4GB RAM
    10GB HDD
  Licensing – 11 interfaces needed to emulate the whole 5G Core Nodes ;
  Additional Licensing Needed for 1M UEs Control Plane
  Additional Licensing Need for 1M UEs User Plane traffic

## Slide 9
WindowsClient/License Server
VChassis
VLOAD Gn
VLOAD GI
Gn
Gi
MGMT
EPC_CORE

## Slide 10: 5G LoadCore Deployment Stages Overview
Prepare VM Images
Download 5G Loadcore Images from our Support Portal https://support.ixiacom.com/software-downloads/236052
Deploy 5G Loadcore Middleware VM and one or Agent VMs on the Public/ Private Cloud infrastructure using our Installation Guide
Provision Loadcore Network Management and Test NIC interfaces
Login to Loadcore Agents and runs agent-setup.sh script and connect to the Middleware VMs
Product Licensing from the Web UI of the Licensing Server
Access Middleware Web UI for Lodcoremanual configurations
Deploy Test Modules in CloudPeak /IxSuiteStore with predefined 5G Core test cases
Run 5G Test cases from the Test Module Library
REST API automation integration with external Net.Ops Orchestrator
Automate Task from Net.Ops to execute Test Cases

## Slide 11: Timeline proposal draft
High Level Design – 2-3 days
Validate Testing Architecture – 1-2 days
Prepare and Provision Deployment environment – 1-2 days
Ixload VE Basic Setup Deployment – 1 week
Loadcore Basic Setup Deployment – 1 week
Cloud Peak + Test Module Setup Deployment – 1 week ;
REST API integration with Net.Ops Orchestrator – 2-3 Days
Test and Validate Automation – from 1 to 3 weeks